## DEC YTD Report for AF&R
Finance YTD CAPEX Project Report - July to December 2023
[9 empty] | Per CPLAN (Infl to 22/23 $'s) | Per CPLAN (Infl to 22/23 $'s)
| Programme | 2023/24 Actuals Dec YTD | 2023/24 Budget Dec YTD | Variance YTD | 2023/24 Full Year Adjusted Budget | % of Full Year Budget Spent | Comments | Ward | 2022/23 Budget | 2023/243 Budget
Assurance, Finance & Risk | Not Applicable | 0 | 15289.9 | 15289.9 | 159486.43 | 0% | Procurement Systems (IN): YTD Budget $0k with Actuals of $0k (Full year budget $123k) - 2023/24 for QLDC wide procurement strategy implementation. Awaiting recruitment of a Procurement Manager. Budget needed but wont be utilised until 2024/25. | District | #REF! | #REF!
[7 empty] | Health and Safety Body Cameras - QLDC: YTD Budget $9k with Actuals of $0k (Full year budget $21k) - Purchase of equipment to be planned. | District
[7 empty] | Parking officer personal transportation: YTD Budget $7k with Actuals of $0k (Full year budget $16k) - The anticipated periphery parking restrictions to be implemented by QLDC Infrastructure Team have not been implemented and there appears to be no short-term plans for this. Surplus budget. | District
COMMUNITY SERVICES | Libraries | 175136.27 | 200724.3 | 25588.03 | 439052.55 | 39.89% | Library Stock - District Wide: YTD Budget $172k with Actuals of $171k (Full year budget $371k) - Programmed to spend 2023/24 | District | #REF! | #REF!
[7 empty] | Frankton Libraries Furniture and Equipment: YTD Budget $6k with Actuals of $0k (Full year budget $13k) - To be used for shelving renewals | Queenstown-Whakatipu
[7 empty] | Whakatipu Libraries Furniture and Equipment: YTD Budget $11k with Actuals of $0k (Full year budget $27k) - To be used for shelving renewals | Queenstown-Whakatipu
[7 empty] | Upper Clutha Libraries Furniture & Equipment: YTD Budget $11k with Actuals of $4k (Full year budget $27k) - To be used for shelving & minor equipment renewals | Wanaka-Upper Clutha
COMMUNITY SERVICES | Parks and Reserves | 590210.87 | 616872.98 | 26662.11 | 2569318.59 | 22.97% | Tracks and Trails Renewals: YTD Budget $165k with Actuals of $111k (Full Year Budget $549k) - Whakatipu focus Gibbston Trail upgrade, Thompson St to Fernhill connection (active travel route B2) and Arrowtown Chinese Village trail realignment. Wanaka focus Millenium trail Wanaka Lakefront to Glendhu Bay and Upper Clutha River trail resurfacing. | District | #REF! | #REF!
[7 empty] | Tree Planting Programme: YTD Budget $91k with Actuals of $74k (Full Year Budget $216k) - Spring planting programme completed. Autumn planting programme underway with planting scheduled Apr/May 2024. | District
[7 empty] | Playground Renewals: YTD Budget $80k with Actuals of $87k (Full year budget $405k) - Whakatipu focus Mcbride Park playground feature replacements and flying foxes (Mcbride, Jardine, Hanleys) to be complete by Mar 2024. Wanaka budget increased in the December Reforecast to enable the Luggate Playground installation (currently under tender process). | District
[7 empty] | Parks Roading Renewals: YTD Budget $10k with Actuals of $166k (Full year budget $644k) - Commitments raised for preseal/reseal. Works to be undertaken Nov 2023-Mar 2024. $50k planned for St Omers Park footpaths, and $50k for Arrowtown reserve sealed footpaths. | District
[7 empty] | Light Pole Replacements & Amenity Lighting: YTD Budget $30k with Actuals of $34k (Full Year Budget $263k) - Replacement of St Omer Park and Wanaka Show Ground Lights planned for delivery Q3. | District
COMMUNITY SERVICES | Venues and Facilities | 182963.21 | 463620.81 | 280657.6 | 864316.33 | 21.17% | Queenstown Events Centre Alpine Aqualand Plant & Equipment Renewals YTD Budget $282k with Actuals of $62k (Full year budget $424k) - $150k ringfenced for Wanaka Basketball hoops, balance likely during May 2024 shutdown | Queenstown-Whakatipu | #REF! | #REF!
[7 empty] | Queenstown Events Centre - Fit Out Renewals: YTD Budget $86k with Actuals of $61k (Full year budget $186k) - Being utilised for minor remedial works. | Queenstown-Whakatipu
[7 empty] | Wanaka Pool - Plant & Equipment Renewals: YTD Budget $49k with Actuals of $12k (Full year budget $108k) - Works to be completed during June shutdown | Wanaka-Upper Clutha
COMMUNITY SERVICES | Buildings | 22245.42 | 25000 | 2754.58 | 25000 | 0% | Ballantyne Rd Rec Cen - Waste Water Site preparation: YTD Budget $25k with Actuals of $16k (Full year budget $25k) - On hold pending Council re-prioritisation process associated with capital planning for draft Long Term Plan 2024-2034. | Wanaka-Upper Clutha | #REF! | #REF!
COMMUNITY SERVICES | Parks and Reserves | 1534731.47 | 3503793.99 | 1969062.52 | 8564741.39 | 17.92% | Wanaka Lakefront Development Plan Stage 2: YTD Budget $228k with Actuals of $222k (Full year budget $325k) - Construction complete by May 2023 with minor works including tiles, now completed Aug 2023. Reviewed of tile defects underway to confirm final close out costs. | Wanaka-Upper Clutha | #REF! | #REF!
[7 empty] | Wanaka Lakefront Development Plan Stage 5: YTD Budget $50k with Actuals of $1k (Full year budget $1.5M) - Stakeholder and community consultation on the concept design complete. Detailed design likely to be completed end February (currently at 90%). Construction procurement possible to commence June with all physical works now likely to be 2024/25 subject to confirmation of additional funding required. | Wanaka-Upper Clutha
[7 empty] | Coronet Forest Revegetation: YTD Budget $1.1M with Actuals of $112k (Full year budget $2.6M) - Planting manager contract awarded. Planting contractor tenders reviewed and to be awarded Feb 2024. $1.9M likely to be deferred in the May Reforecast in line with proposed work programme. | Arrowtown-Kawarau
[7 empty] | Water Sports Facility & Parking - Wanaka: YTD Budget $235k with Actuals of $64k (Full year budget $624k) - The Wanaka-Upper Clutha Community Board has agreed scope change in May to change focus to include a new bridge across stoney creek as a priority with remaining budget to include carparking. Procurement plan completed and tenders now under review. Contract to be awarded January with works to commence February. | Wanaka-Upper Clutha
[7 empty] | Glenorchy Carpark & Marina Improvements: YTD Budget $319k with Actuals of $44k (Full year budget $723k) - Community engagement complete with concept plans approved April 2023. Design complete. Currently review pricing which is above budget. Construction planned 2024/25 subject to budget increase/transfers. | Queenstown-Whakatipu
[7 empty] | Toilet Renewals: YTD Budget $301k with Actuals of $131k (Full year budget $631k) - Contract for implementation of toilets at Marine Parade, Shotover Country Sportsfield (planned for delivery May/June) and Northlake (planned for delivery March). | District
COMMUNITY SERVICES | Venues and Facilities | 171612 | 173483 | 1871 | 323483 | 53.05% | Frankton Golf Course Reconfiguration: YTD Budget $150k with Actuals of $96k (Full year budget $300k) - Completion of golf course works Jan-Mar 2024 to be offset with Waka Kotahi funding ($470k). Club house works planned May 2024. | Queenstown-Whakatipu | #REF! | #REF!
[7 empty] | Queenstown Events Centre - Carpark Reconfiguration: YTD Budget $23k with Actuals of $76k (Full year budget $23k) - Masterplan concept design completed 2022/23. On hold. Deferred to 2026/27 due to Longterm Plan 2024-2034 baseline approach. PM costs to be reallocated. | Queenstown-Whakatipu
CORPORATE SERVICES | Information Management | 450299.22 | 700065.59 | 249766.37 | 1497519.67 | 30.07% | Enterprise System: YTD Budget $278k with Actuals of $262k (Full year budget $603k) - Work scheduled to be delivered by 30/06/24 - Consultants supporting the TechnologyOne project pipeline; Internal resource backfill to support TechnologyOne CiA transition programme and Sentient. | District | #REF! | #REF!
[7 empty] | ICT Projects: YTD Budget $130k with Actuals of $30k (Full year budget $286k) - Work scheduled to be delivered by 30/06/24 - Laptop cybersecurity upgrade, Cloud maturity support, backup audit, Digital Strategy Support, Information Management Transformation project support | District
[7 empty] | ICT Network: YTD Budget $107k with Actuals of $27k (Full year budget $236k) - Work scheduled to be delivered by 30/06/24 - Network improvement projects, IoT Platform enhancements, Wi-Fi and switch upgrades | District
CORPORATE SERVICES | Libraries | 33465.11 | 122586.35 | 89121.24 | 269689.92 | 12.41% | Library Systems: YTD Budget $123k with Actuals of $33k (Full year budget $270k) - Libraries Website $80k, Security gates Arrowtown and Hawea Mar/Apr ($40k), Humanforce project Jan/Feb start $21k, RFID wands $18k. | District | #REF! | #REF!
CORPORATE SERVICES | Not Applicable | 14635 | 8737.1 | -5897.9 | 20968.99 | 69.79% | Emergency Management YTD Budget $9k with Actuals of $15k (Full year budget $21k) - Data projector emergency operations equipment purchased. | District | #REF! | #REF!
INFRASTRUCTURE | Buildings | 259305.35 | 385598.84 | 126293.49 | 1487460.02 | 17.43% | Gorge Rd Office Civic Building - Renewal: YTD Budget $108k with Actuals of $96k (Full year budget $244k) - Toilet reconfiguration to be complete Jan 2024, furniture/desks replacements ongoing. | Queenstown-Whakatipu | #REF! | #REF!
[7 empty] | Pontoon jetty renewals: Whakatipu YTD Budget $0k with Actuals of $0k (Full year budget $323k) - Condition assessments completed by WSP across waterways structures. Quantity Surveyor pricing and prioritisation completed. Procurement plan underway with Request For Proposals expected to go to market by Feb 2024. Const likely to commence by Apr 2024 across 3 sites (Kingston, Sunshine Bay & Bobs Cove Jetties). | Queenstown-Whakatipu
[7 empty] | Wanaka Jetty 147 replacement: YTD Budget $10k with Actuals of $0k (Full year budget $241k) - Condition assessments completed by WSP across waterways structures. Quantity Surveyor pricing and prioritisation completed. Procurement plan underway with Request For Proposals expected to go to market by Feb 2024. Const likely to commence by Apr 24 across 3 sites (Kingston, Sunshine Bay & Bobs Cove Jetties). | Wanaka-Upper Clutha
[7 empty] | Healthy Homes: YTD Budget $161k with Actuals of $84k (Full year budget $271k) - Phase 2 Arrowtown/Wanaka well underway with further works still to be completed awaiting quotes and approvals. | District
INFRASTRUCTURE | Camp Grounds | 525 | 0 | -525 | 66380.8 | 0.7909% | Campgrounds - Minor Capex: YTD Budget $0 with Actuals of $1k (Full Year Budget $66k) - No works identified/required at present. | District | #REF! | #REF!
INFRASTRUCTURE | Libraries | 102523.92 | 67985.92 | -34538 | 86009.8 | 119.2% | Libraries Building Renewals YTD Budget $66k with Actuals of $88k (Full Year Budget $81k) - Emergency works completed to remove borer and reinstate wall linings & floors at Kingston Library. | District | #REF! | #REF!
INFRASTRUCTURE | Transport | 1773969.93 | 2717126.97 | 943157.04 | 8880074.6 | 19.98% | Sealed road resurfacing: YTD Budget $530k with Actuals of $870k (Full Year Budget $2.1M) - Downer contract programmed for completion Jan-Apr 2024. | District | #REF! | #REF!
[7 empty] | Sealed road pavement rehabilitation: YTD Budget $473k with Actuals of $83k (Full Year Budget $2.5M) - Contract awarded for Cardrona Valley Road and Lower Shotover Road rehabilitation works with works programmed for Dec-Apr 2024 Sealing season. | District
[7 empty] | Unsealed road metalling: YTD Budget $587k with Actuals of $4k (Full year budget $1.4M) - Budgets aligned with Waka Kotahi funding. Rolling Downer contract to complete works. | District
[7 empty] | Butlers Green Retaining Wall: YTD Budget $22k with Actuals of $10k (Full year budget $50k) - The remaining $50k budget is required to finalise the heritage impact assessment and design options. It is important to note that the established budget will be insufficient for any likely solution so this deferral signals an intention to invest only. The budget will be updated when a preferred option is selected and costed. | Arrowtown-Kawarau
INFRASTRUCTURE | Venues and Facilities | 11400.33 | 29677.06 | 18276.73 | 120851.85 | 9.433% | Wanaka Arts Centre - Building Renewals YTD Budget $14k with Actuals of $0k (Full year budget $50k) - Internal/External painting planned 2023/24. Pricing received above budget. Scope under review prior to award of contract. | Wanaka-Upper Clutha | #REF! | #REF!
[7 empty] | Arrowtown Hall - Renewals: YTD Budget $0k with Actuals of $0k (Full year budget $24k) - Required for air con refurbishment | Arrowtown-Kawarau
INFRASTRUCTURE | Waste Management | 109125.34 | 440750.04 | 331624.7 | 1332460.65 | 8.19% | Existing Waste Site Consenting: YTD Budget $161k with Actuals of $9k (Full year budget $627k) - Victoria Flats Landfill consent expires 2032. Morrison Low engaged to draft Request For Proposals, which is now targeted for Q3 2023/24, followed by procurement of a consenting specialist. Also awaiting remediation pricing including consenting for Luggate closed landfill and Tuckers Beach. | District | #REF! | #REF!
[7 empty] | Existing Whakatipu Waste Facilities: YTD Budget $246k with Actuals of $99k (Full year budget $513k) - Proposal received from Waste Management on upgrades required. $403k commitments incl MRF Pit floor, heating, rollers, belts & pipes. MRF prelim assessment/design for Frankton Transfer station underway. | Queenstown-Whakatipu
[7 empty] | Public Place Waste Bins: YTD Budget $30k with Actuals of $0k (Full year budget $159k) - 2023/24 focus on install of bins purchased 2022/23 (expected Jan to Mar 2024). | District
INFRASTRUCTURE | Storm Water | 185415.34 | 628168.62 | 442753.28 | 1234122.44 | 15.02% | 3 Waters Renewals: YTD Budget $2.5M with Actuals of $2.4M (Full Year Budget $4.4M - Renewals Works programmed to spend full 2023/24 budget. Rockabilly Gully Erosion Protection (SW): YTD Budget $164k with Actuals of $1k (Full year budget $308k) - Long lead time for technical services currently indicated; rephased to reflect more realistic start date. Procurement for business case inputs and design to be engaged via legal team due to litigation underway. | District | #REF! | #REF!
INFRASTRUCTURE | Waste Water | 546849.3 | 1108034.65 | 561185.35 | 2646308.04 | 20.66% |  |  | #REF! | #REF!
INFRASTRUCTURE | Water Supply | 1777859.3 | 1024518.07 | -753341.23 | 974184.45 | 182.5% |  |  | #REF! | #REF!
INFRASTRUCTURE | Not Applicable | 12103.01 | 0 | -12103.01 | 0 | 0% | 3W Reform Stimulus close out - Costs to be reallocated to other renewals | District | #REF! | #REF!
INFRASTRUCTURE | Buildings | 160498.52 | 901432.01 | 740933.49 | 1702766.7 | 9.426% | Performing Arts Centre YTD Budget $483k with Actuals of $19k (Full year budget $524k) - Remaining budget for removal of QPAC to relocate to Country Lane (circa $0.4M) and demolition/temporary car park works. Pending consent prior to removal. Likely early 2024. | Queenstown-Whakatipu | #REF! | #REF!
[7 empty] | Luggate Hall Replacement: YTD Budget $183k with Actuals of $72k (Full year budget $361k) - Practical completion Nov 2022. Opened in December. Awaiting invoice to close out final claim to resolve Storm water issues. Minor close out works to follow. | Wanaka-Upper Clutha
[7 empty] | Stanley St playcentre relocation: YTD Budget $146k with Actuals of $0k (Full year budget $350k) - Ministry of Education has recently advised a delay in their programme, this is likely to be by Feb 2024. This is a one off payment of $350,000 towards the new facility. | Queenstown-Whakatipu
[7 empty] | Frankton Library Fitout of leased space: YTD Budget $33k with Actuals of $10k (Full year budget $203k) - Design being modified for new leased area. Some savings expected due to reduced scope. Procurement expected early 2024. | Queenstown-Whakatipu
INFRASTRUCTURE | Waste Management | 569210.53 | 681006.51 | 111795.98 | 4250316.17 | 13.39% | Whakatipu New Waste Facilities: YTD Budget $10k with Actuals of $52k (Full year budget $2.8M) - Budget used for land purchase in Wanaka Jan 2024. | Wanaka-Upper Clutha | #REF! | #REF!
[7 empty] | Organic Waste Management: YTD Budget $263k with Actuals of $92k (Full year budget $467k) - Forecast to spend $651k which is an additional $184k that will be reimbursed by Ministry for the Environment (milestone dates Feb/Mar 24) to support kerbside collections, Grow Wanaka and Zero Waste Glenorchy initiatives | District
[7 empty] | Zero Waste District Programme: YTD Budget $301k with Actuals of $412k (Full Year Budget $695k) - Service agreements in place which will incur milestone payments (Resourceful communities $212k, Wanaka Community Workshop $41k, One Bike Lightfoot Initiative $39k, Kiwi Harvest $38k, Zero Waste Event work $30k, WAO Circular Economy Programme $108k). | District
INFRASTRUCTURE | Storm Water | 359230.86 | 531865.65 | 172634.79 | 1246341.48 | 28.82% | Catchment Mgt Plans - Whakatipu & Wanaka YTD Budget $177k with Actuals of $90k (Full Year Budget $389k) - Contract committed to spend full amount across Whakatipu and Wanaka. | District | #REF! | #REF!
[7 empty] | Investigations - Whakatipu & Wanaka: YTD Budget $160k with Actuals of $95k (Full Year Budget $382k) - Contract with E3 Scientific commenced March 2023 for $160k across Whakatip and Wanaka across 21 locations over 2 years. A contract for Storm Water level monitoring for $160k also commenced in May to run through 2023/24. | District
[7 empty] | Modelling - Whakatipu & Wanaka: YTD Budget $92k with Actuals of $109k (Full Year Budget $201k) - Commitments raised for modelling to feed into CMP's. | District
INFRASTRUCTURE | Waste Water | 367774.04 | 1765856.05 | 1398082.01 | 2691825.78 | 13.66% | Project Pure Aeration Grid Renewal: YTD Budget $1.2M with Actuals of $37k (Full year budget $1.3M) - Contract in final stages of negotiation. Works includes a significant supply component which will be expended early in the contract duration. | Wanaka-Upper Clutha | #REF! | #REF!
[7 empty] | Masterplanning Waste Water: YTD Budget $140k with Actuals of $39k (Full year budget $308k) - Eastern corridor and Arrowtown Waste Water Optimisation study works ongoing. Masterplanning ongoing related to Gordon Road Pump station. | District
[7 empty] | Gordon Road Pump Station upgrade: YTD Budget $55k with Actuals of $24k (Full year budget $196k) - Procurement plan approved. Procurement to commence early 2024. | Queenstown-Whakatipu
INFRASTRUCTURE | Water Supply | 821149.18 | 1352527.24 | 531378.06 | 18861913.66 | 4.353% | Cardrona Water Supply Scheme YTD Budget $55k with Actuals of $94k (Full year budget $15.1M) - QLDC is required to make payment to the developer 2023/24 forecast for Feb 2024. | Wanaka-Upper Clutha | #REF! | #REF!
[7 empty] | Demand Management - Hawea Water Supply: YTD Budget $216k with Actuals of $51k (Full year budget $1.5M) - Budget brought forward in the Dec Reforecast. A preferred contractor has been selected, and meter installation is programmed for commencement within the current financial year. | Wanaka-Upper Clutha
[7 empty] | Wanaka Scheme Upgrades Water Supply: YTD Budget $35k with Actuals of $7k (Full year budget $120k) - 23/24 budget being utilised for the UV rapid deployment project. Emergency installations at Western Intake, Beacon Point, Wanaka Airport, Corebridge and Luggate to be completed throughout 2024. | Wanaka-Upper Clutha
[7 empty] | Luggate Reservoir Capacity Water Supply: YTD Budget $70k with Actuals of $69k (Full year budget $290k) - Land purchase due for settlement Jan 2024 (circa $190k) following consenting/designation. Project to be placed on hold pending future funding for construction. | Wanaka-Upper Clutha
[7 empty] | Hydro Model & Systems Performance - Districtwide WS: YTD Budget $205k with Actuals of $42k (Full year budget $479k) - Modelling underway on Queenstown bores and specific developments (Silver Creek / Coneburn) and Ladies Mile. | District
INFRASTRUCTURE | Transport | 6441841.29 | 8044535.92 | 1602694.63 | 20069794.94 | 32.1% | Road to Zero Minor Improvements Programme LCLR YTD Budget $4.4M with Actuals of $4.1M (Full year budget $10.1M) - Construction underway/scheduled for Hawthorne Rd, Glenorchy Corridor, Lower Shotover Rd, Arrowtown RTZ, Riverbank/Ballantyne, Golf Rd, Capell Ave, Wanaka Corridor, Anderson/Aubrey, Rata St, Aubrey Rd & Cardrona Village. Waka Kotahi Sub 51% sub budget. | District | #REF! | #REF!
[7 empty] | Wanaka Pool to School Active Travel: YTD Budget $1.6M with Actuals of $727k (Full year budget $5.0M) - Works programmed for Stage 2 Kellys flat to Hedditch Oct 2023 to Mar 2024 ($1.8M) of which $1.5M is Transport Choice Sub funded. Stage 3 Ballantyne to Golf course rd ($800k) & Stage 4 State Highway crossing ($1.2M) are pending procurement. | Wanaka-Upper Clutha
[7 empty] | Whakatipu Active Travel Low Cost Low Risk: YTD Budget $548k with Actuals of $43k (Full year budget $1.4M) - Route B2 Thompson Street works due for completion March 2024 ($1.4M). | Queenstown-Whakatipu
[7 empty] | Wanaka Active Travel Low Cost Low Risk: YTD Budget $319k with Actuals of $537k (Full year budget $601k) - Anderson Rd Active travel to be completed Jan 2024. Minor close out works to follow. | Wanaka-Upper Clutha
[7 empty] | Whakatipu Public Transport Low Cost Low Risk: YTD Budget $162k with Actuals of $158k (Full year budget $662k) - Tranche 2 construction contract practical completion reached June 2023, with minor close out works to follow 2023/24 along with Tranche 3 Design and consultation. | Queenstown-Whakatipu
[7 empty] | Wanaka Masterplan Update: YTD Budget $206k with Actuals of $278k (Full year budget $618k) - Contract for network optimisation single stage business case commenced Sept 2023. Waka Kotahi Sub budget. | Wanaka-Upper Clutha
INFRASTRUCTURE | Venues and Facilities | 9609.51 | 0 | -9609.51 | 368254.45 | 2.609% | Building Management System: YTD Budget $0k with Actuals of $8k (Full year budget $367k) - Designs complete. Pending site visits and awaiting delivery of equipment. Implementation expected to commence by March 2024. | District | #REF! | #REF!
INFRASTRUCTURE | Not Applicable | 247816.72 | 301478.84 | 53662.12 | 381395.34 | 64.98% | Queenstown Priority Growth Corridors: YTD Budget $167k with Actuals of $160k (Full year budget $228k) - Establishment Report complete. Recruitment for a programme manager to commence early 2024 | Queenstown-Whakatipu | #REF! | #REF!
[7 empty] | Wanaka Airport Masterplan (CAA Compliance): YTD Budget $135k with Actuals of $88k (Full year budget $153k) - Draft Capital Plan and Functional Strategy delivered and integrated into draft Long Term Plan 2024-2034 preparations. Part 139 compliance deliverables have triggered the need to review WKA management structure and the current services agreement in place. Investigative work underway to explore alternatives. | Wanaka-Upper Clutha
PMO - Project Management Office | Waste Management | 409431.6 | 121979 | -287452.6 | 1245129 | 32.88% | Wanaka New Waste Facilities: YTD Budget $122k with Actuals of $409k (Full year budget $1.2M) - Design contract awarded Nov and commenced concept design, due to complete Feb 2024. Deposit for land purchase $336k paid in December with balance 31 January to be split with Whakatipu new Waste facilities. | Wanaka-Upper Clutha | #REF! | #REF!
PMO - Project Management Office | Storm Water | 511063.15 | 96000 | -415063.15 | 557281 | 91.71% | Aubrey Rd Rec Reserve Storm Water detention pond: YTD Budget $1k with Actuals of $384k (Full year budget $430k) - Detailed design and construction of Aubrey Rd pipeline complete. Balance of project to be placed on hold until future funding is available for construction of the Kellys Flat detention pond. | Wanaka-Upper Clutha | #REF! | #REF!
[7 empty] | Kingston HIF New Scheme Storm Water: YTD Budget $95k with Actuals of $127k (Full year budget $127k) - Design and procurement of the stormwater scheme is being managed by the developer. Detailed design is complete and the earthworks consent has been granted. The next step is procurement/construction. | Queenstown-Whakatipu
PMO - Project Management Office | Waste Water | 12112878.16 | 13167802.89 | 1054924.73 | 23393902.73 | 51.78% | Marine Parade Pump Station Electrical Upgrade YTD Budget $63k with Actuals of $60k (Full year budget $65k) - Detailed design is complete and notice of requirement (NOR) has been lodged to designate the new location for the pump station. Project to be placed on hold pending future funding for construction. | Queenstown-Whakatipu | #REF! | #REF!
[7 empty] | Project Pure Upgrade Waste Water Project Pure Upgrade: YTD Budget $3.7M with Actuals of $3.5M (Full year budget $4.2M) - Construction commenced April 2022 and completed Dec 2023. Commissioning scheduled for completion Feb 2024. | Wanaka-Upper Clutha
[7 empty] | Upper Clutha Conveyance Scheme: YTD Budget $633k with Actuals of $385k (Full year budget $1.0M) - Detailed design has commenced and is planned to be completed by early to mid 2025. The design programme has been extended to analyse and incorporate potential design changes required to align with the latest Draft QLDC population forecasts. The project team is reviewing the overall programme to understand any potential impacts to the originally forecast practical completion date, and liaising closely with the Infrastructure Acceleration Fund management team within Kainga Ora regarding likely changes to funding milestones. | Wanaka-Upper Clutha
[7 empty] | Project Shotover Plant Upgrade: YTD Budget $5.9M with Actuals of $6.2M (Full year budget $14M) - Construction contract awarded to McConnell Dowell. Physical works commenced Aug 2023 and due to be completed Dec 2025. | Queenstown-Whakatipu
[7 empty] | Kingston HIF new scheme Waste Water: YTD Budget $92k with Actuals of $149k (Full year budget $146k) - Detailed design is underway and is expected to be completed late 2024 / early 2025. | Queenstown-Whakatipu
[7 empty] | North Wanaka Conveyance Waste Water: YTD Budget $104k with Actuals of $151k (Full year budget $250k) - The project is being delivered in two stages; (1) Aubrey Road conveyance, and (2) Beacon Point Rd Pump Station. Stage 1 completed June 2023. Stage 2 pump station designation appealed by submitters at hearing with mediation undertaken Nov 23 (waiting for the experts report to evaluate whether the Appeal can be resolved). Potential for budget requiring b/f to complete chip seal to improve the overall quality to Aubrey Rd. | Wanaka-Upper Clutha
[7 empty] | CBD to Frankton Conveyance Waste Water: YTD Budget $2.5M with Actuals of $1.5M (Full year budget $3.2M) - Sewer relining works underway April 2023 with forecast completion date by April 2024. Detailed design for the planned new rising main has commenced, with construction anticipated to commence by June 2024 subject to securing necessary planning permissions. | Queenstown-Whakatipu
[7 empty] | Robins Road Conveyance Upgrade Waste Wwater: YTD Budget $174k with Actuals of $189k (Full year budget $580k) - Detailed design is underway, with construction forecast to commence in 24/25. | Queenstown-Whakatipu
PMO - Project Management Office | Water Supply | 9446898.26 | 9325065.3 | -121832.96 | 20463439.27 | 46.16% | Shotover Country New Water Treatment Plant Shotover Country New WTP (WS) YTD Budget $235k with Actuals of $313k (Full year budget $549k) - Physical works complete. Practical completion issued January 2024. | Queenstown-Whakatipu | #REF! | #REF!
[7 empty] | Glenorchy Reservoir upgrade: YTD Budget $2.4M with Actuals of $1.9M (Full year budget $2.4M) - The new reservoirs were commissioned in Dec 2023. Practical completion is scheduled for January 24. | Queenstown-Whakatipu
[7 empty] | Beacon Point new Reservoir: YTD Budget $4.5M with Actuals of $3.4M (Full year budget $5.6M) - Construction commenced in December 2022 and main Reservoir tank works completed December 2023. Budget of $1.5M added in the December reforecast to complete construction of earth bund to screen future Water Treatment Plant. | Wanaka-Upper Clutha
[7 empty] | Luggate Water Supply Scheme: YTD Budget $158k with Actuals of $112k (Full year budget $230k) - Detailed design completed March 2023. Project will be placed on hold until future funding is available for construction. | Wanaka-Upper Clutha
[7 empty] | Kingston HIF New Scheme Water Supply: YTD Budget $74k with Actuals of $61k (Full year budget $104k) - Detailed design of the scheme is complete, with Stage 1 ready for construction procurement (Stage 1 includes construction of a new water treatment plant, reservoir, and rising and falling water supply main). The next step is to go to market for construction. | Queenstown-Whakatipu
[7 empty] | Quail Rise Reservoir: YTD Budget $176k with Actuals of $165k (Full year budget $190k) - Detailed design complete and planning/designation activities ongoing. Project will be placed on hold until future funding is available for construction. | Queenstown-Whakatipu
[7 empty] | Glenorchy Water Treatment Plant: YTD Budget $113k with Actuals of $70k (Full year budget $113k) - Detailed design and consent application scheduled for completion Feb 2024. Project will be placed on hold until future funding is available for construction. | Queenstown-Whakatipu
[7 empty] | Western Wanaka Level of Service Water Supply: YTD Budget $5k with Actuals of $16k (Full year budget $408k) - Practical completion March 2023 for main Heb contract capitalised 2022/23. Agreed scope changes to include delivery of other parts of the ultimate conveyance route (to be funded from the project's forecast surplus) have been approved. Works for stage 2 (Alpha Series pipeline) has now been completed with stage 3 (further extensions to Alpha Series pipeline) pending confirmation from developer on engineering acceptance of subdivision works. | Wanaka-Upper Clutha
[7 empty] | Cardrona Water Supply Scheme Pipeline: YTD Budget $337k with Actuals of $411k (Full year budget $2.4M) - Construction contract commenced Nov 2023, with forecast completion May 2024. | Wanaka-Upper Clutha
[7 empty] | Compliance Response - UV Treatment Water Supply: YTD Budget $1.4M with Actuals of $3.0M (Full year budget $8.5M) - Fernhill, Western Intake UV treatment completed Dec 2023. Beacon Pt scheduled for early Feb completion. Smaller UV locations to be rolled out over remainder of year (Corbridge, Wanaka Airport, Luggate, Glenorchy). Two Mile intake subject to planning requirements. | District
PMO - Project Management Office | Transport | 2257548.59 | 2797082 | 539533.41 | 7436299.76 | 30.36% | Whakatipu Active Travel Network YTD Budget $38k with Actuals of $26k (Full year budget $186k) - No further expenditure planned for 2023/24; opportunities to repurpose balance of funding to other active travel assets being explored. | Queenstown-Whakatipu | #REF! | #REF!
[7 empty] | Arthurs Point to CBD Active Travel: YTD Budget $2.8M with Actuals of $2.2M (Full year budget $7.3M) - Construction commenced September 2023 and is forecast to complete by May 2024. | Arrowtown-Kawarau
PMO - Project Management Office | Buildings | 1972391.42 | 2083204 | 110812.58 | 2083325.82 | 94.68% | Paetara Aspiring Central: YTD Budget $2.1M with Actuals of $2.0M (Full year budget $2.1M) - Construction commenced April 2023 and practical completion reached September 2023. Minor close out works to follow. | Wanaka-Upper Clutha | #REF! | #REF!
PMO - Project Management Office | 3 Waters | -5458.89 | 0 | 5458.89 | 0 | 0% | Programme Management Costs reallocated to projects monthly. | District | 0 | 0
Strategic Projects | Manawa - Project Connect & Civic Heart | 91914.19 | 31860.25 | -60053.94 | 73745.34 | 124.6% | Council office: Continuing to work with Ngāi Tahu Property through the 2019 Partnering Agreement, the aim of which is to agree a development plan for the Stanley Street site to deliver an integrated development of community assets and commercial buildings. Councillors have approved community consultation on some initial elements of this proposal and will consider the outcome of that consultation in early 2024. | Queenstown-Whakatipu | #REF! | #REF!
| 516 Ladies Mile Community Centre | 8993.07 | 0 | -8993.07 | 0 | 0% | Queenstown Town Centre Arterials - CIP Stage 1 - Three waters work is complete in Gorge road (excl, WW relining/bursting), as well as in the northern half of Melbourne Street. Construction works are continuing across all construction zones of the Arterial project, with a focus on underground services, structures and retaining walls. As previously reported, the project continues to be challenged by price escalation in the construction sector and resourcing of skilled labour. Providing greater certainty of the future cost risk remains a high priority for The Alliance. The cost to complete is currently under review, with any impact on timing and budget subject to further review and validation over coming months. Adjustments to forecast expenditure will be sought when a final position is determined; it is anticipated a bring forward from 2024/25 will be required in the second 2023/24 Capital Reforecast to align with the Alliance’s likely cashflow within the current financial year |  | #REF! | #REF!
Strategic Projects | Queenstown Strategic Land Purchases | 0 | 0 | 0 | 0 | 0% | For reallocation of 2A/B Shotover St Land and Ballarat St Apartment purchases that were allocated to Arterials but were purchased for strategic purposes and are assets likely to be onsold. | District | #REF! | #REF!
Strategic Projects | CIP - Crown Infrastructure Fund | 25706866.42 | 28229442.23 | 2522575.81 | 31685580.73 | 81.13% | Queenstown Arterial Stage 1: YTD Budget $23.8M with Actuals of $21.8M (Full year budget $27.6M) - Gorge Road has been resurfaced and has been opened in an interim arrangement. Works on retaining walls are underway on Glebe and Malaghan Street and St Joseph's Wall works are significantly progressing with precast panel placement ongoing. Three Waters work is effectively complete on Gorge Road. Following a review from the Alliance board on 5 December 2023, an updated cost and timeline for project completion has been presented. This increase in the estimated cost to complete the project is the topic of a report to the proposed increase will be presented to Full Council meeting of 15 February 2024. Queenstown Street Upgrades: As at 30 December 2023 Project Construction is complete with minor snagging works (faults and omissions) underway in parallel to submission of the final Quality Assurance Documents | Queenstown-Whakatipu | #REF! | #REF!
Strategic Projects | Lakeview Development - Subdivision Works | 3552754.25 | 3411196.79 | -141557.46 | 4335868.83 | 81.94% | Infrastructure works internal to the subdivision have been completed. The final project close out and handover is scheduled to be complete by March/April 2024 but is reliant on completion of Ancillary project work. Note a $1.0M deferral to 2024/25 was approved in the December Reforecast which was required to align payment with the developer-delivered swails due for completion in 2024/25. | Queenstown-Whakatipu | #REF! | #REF!
Strategic Projects | Lakeview Development - Site Clearance | 40671.42 | 220000 | 179328.58 | 2628849.33 | 1.547% | The Alliance has completed the known asbestos removal work. Remaining vacated cabins on site expected to be removed in 2024, tender assessment has been competed and contractor anticipated to commence works in March 2024. Any remaining budget post completion of remaining cabin clearance to be discussed at Lakeview Project Control Group to confirm if any funding is required for future years. | Queenstown-Whakatipu | #REF! | #REF!
Strategic Projects | Lakeview Ancillary | 5810634.56 | 5366527.38 | -444107.18 | 6390781.34 | 90.92% | The Alliance current programme anticipates completion of Man/Thompson St in Feb/March 2024, with final handover in March/April. Awaiting confirmation of revised dates to complete existing Isle St surface upgrades. | Queenstown-Whakatipu | #REF! | #REF!
| TOTAL | 78848092.24 | 90660896.25 | 11812804.01 | 181428241.19 | 43.46% |  |  | #REF! | #REF!
|  | #REF! | #REF! | 0 | #REF! |  |  |  | #REF! | #REF!